# ANNEX AK

## ERT Field Lead Pre-Deployment Checklist

NEW IN v3.0 — Aligned to SOP v5.1

Reference: ERT ACTIVATION AND MOBILISATION §11 | Output: FLPD-01

### 1. Purpose

Specific checklist for the ERT Field Lead covering responsibilities that must be completed before departure. Supplements the general ERT Mobilisation Checklist (Annex A) with Field Lead-specific obligations.

| Document Ref: |  | Date: |  |
| --- | --- | --- | --- |
| Prepared By: |  | Mission: |  |

### 2. Pre-Departure Actions (72 hours to departure)

| # | Action | Deadline | Status | Notes |
| --- | --- | --- | --- | --- |
| 1 | Confirm personal availability to ERT Coordinator within 24 hours of notification | 72hr before departure | ☐ |  |
| 2 | Sign attestation: Code of Conduct, medical fitness, conflict-of-interest declaration, PSEA acknowledgement | 72hr before departure | ☐ |  |
| 3 | Attend full Pre-Deployment Briefing (all 9 components per ERT ACTIVATION AND MOBILISATION §8) | 48hr before departure | ☐ |  |
| 4 | Review and sign Pre-Deployment Briefing Record (Annex C) | 48hr before departure | ☐ |  |
| 5 | Convene ERT team set-up meeting: confirm roles, communication protocols, reporting lines | 36hr before departure | ☐ |  |
| 6 | Verify team composition against mission order; confirm all members have valid travel documents and visas (cross-check Annex D) | 36hr before departure | ☐ |  |
| 7 | Verify personal mission kit completeness: ICT equipment, sat-phone, PPE, personal medical kit | 24hr before departure | ☐ |  |
| 8 | Confirm receipt of Mission Information Pack (Annex AI) for self and all team members | 24hr before departure | ☐ |  |
| 9 | (Annex AJ) issued to all team members | 24hr before departure | ☐ |  |
| 10 | Confirm travel logistics: flights, ground transport, accommodation details with SHOC HR / Deployment Coordinator | 24hr before departure | ☐ |  |
| 11 | Confirm communication with NDMA DRR Focal Point: arrival time, reception point, arrival protocol, initial briefing schedule | 12hr before departure | ☐ |  |
| 12 | Confirm security briefing acknowledged and evacuation plan understood by all team members | 12hr before departure | ☐ |  |
| 13 | Declare any spouse/partner on same deployment to ERT Coordinator | 12hr before departure | ☐ |  |
| 14 | Final check: SHOC ERT Portal status updated to MOBILISED; all personal documents verified | departure day | ☐ |  |
| 15 | Assume transit command; ensure all team members accounted for at departure point | departure day | ☐ |  |

### 3. In-Transit Responsibilities

| # | Action | Status | Notes |
| --- | --- | --- | --- |
| 1 | Maintain headcount of all ERT members during transit | ☐ |  |
| 2 | Ensure team has emergency contact numbers accessible during transit | ☐ |  |
| 3 | Contact NDMA DRR Focal Point with updated ETA upon boarding and upon landing | ☐ |  |
| 4 | Report any transit disruptions immediately to ERT Coordinator | ☐ |  |
| 5 | Confirm team arrival to SHOC Situation Room upon reaching destination | ☐ |  |

### 4. Field Lead Declaration

I confirm that all pre-deployment actions listed above have been completed and that the ERT is ready for deployment.

| Prepared By | Approved By |
| --- | --- |
| Name: ___________________________ Designation: ____________________ Signature: ______________________ Date: ___________________________ | Name: ___________________________ Designation: ____________________ Signature: ______________________ Date: ___________________________ |