# Annex 6.2-H: ETC Coordination Procedures and Contacts

## ETC Activation Procedures

| Step | Action | Responsible | Timeline |
| --- | --- | --- | --- |
| 1 | Identify telecommunications gap requiring ETC support | ICT Officer / Head of Ops | As identified |
| 2 | Contact ETC Global Coordinator (WFP) for initial consultation | ICT Officer | Within 2 hours |
| 3 | Submit formal request via ETC request mechanism | Head of Operations | Within 6 hours |
| 4 | Coordinate with emergency.lu if satellite support needed | ICT Officer | Within 12 hours |
| 5 | Activate Crisis Connectivity Charter if applicable | Executive Director | Within 24 hours |
| 6 | Receive and deploy ETC equipment | ICT Officer / Field Team | Per ETC timeline |
| 7 | Integrate ETC services with SHOC systems | ICT Officer | Within 24 hours of receipt |
| 8 | Coordinate with WIDER for bandwidth management | ICT Officer | Ongoing |
| 9 | Report usage and status to ETC coordination | ICT Officer | Weekly during activation |

## ETC Key Contacts

| Organisation | Contact Role | Phone | Email |
| --- | --- | --- | --- |
| WFP ETC | Global ETC Coordinator |  | etc@wfp.org |
| WFP ETC | Regional ETC Coordinator (ESA) |  |  |
| emergency.lu | Duty Manager |  | operations@emergency.lu |
| Ericsson Response (WIDER) | Operations Centre |  |  |
| GSMA Crisis Connectivity | Coordinator |  |  |
| Inmarsat | Humanitarian Desk |  |  |
| Starlink (via Paratus) | Enterprise Support |  |  |
| UNDSS | Regional Security Advisor |  |  |

## Crisis Connectivity Charter Activation Criteria

| ✓ | Activation Criteria |
| --- | --- |
| ☐ | Major natural disaster affecting telecommunications infrastructure |
| ☐ | Government request for international telecommunications assistance |
| ☐ | Multiple affected countries in SADC region |
| ☐ | Existing telecommunications infrastructure insufficient for humanitarian response |
| ☐ | Formal request submitted through ETC coordination mechanism |
| ☐ | SHOC activation at M2 or M3 level |