# Annexes: SOP 5.2: Staff Welfare and Support

# Annex 5.2-A: Welfare Support Flowchart

Purpose: Visual workflow for welfare support across the deployment cycle.

## Pre-Deployment Phase (Preparedness–Standby)

| Step | Action | Timeline | Output | Next |
| --- | --- | --- | --- | --- |
| 1 | Medical fitness verification | ≥2 weeks | Clearance confirmed | → Step 2 |
| 2 | Insurance activation | ≥1 week | Coverage active | → Step 3 |
| 3 | MHPSS readiness check | ≥1 week | Psych clearance | → Step 4 |
| 4 | Welfare briefing | ≥3 days | Briefing signed | → Step 5 |
| 5 | PPE and safety equipment | ≥3 days | Equipment issued | → Step 6 |
| 6 | Security briefing | ≥1 day | Security cleared | → Deploy |

## During Deployment Phase (Dispatch)

| Activity | Frequency | Responsible | Escalation |
| --- | --- | --- | --- |
| Daily welfare check-in | Daily | ERT Team Lead | → Welfare Officer |
| Rest rotation monitoring | Daily | ERT Team Lead | → Head of Ops |
| Nutrition provision | 3x daily | Logistics | → Welfare Officer |
| Medical standby | Continuous | Medical Officer | → Medevac |
| Peer support activation | As needed | Peer Supporters | → MHPSS Spec |
| Family communication | Weekly minimum | Individual | → HR Officer |

## Post-Deployment Phase

| Step | Action | Timeline | Output | Next |
| --- | --- | --- | --- | --- |
| 1 | Medical assessment | ≤3 days | Health cleared | → Step 2 |
| 2 | Psychological debrief | ≤7 days | Debrief complete | → Step 3 |
| 3 | Welfare survey | ≤7 days | Feedback collected | → Step 4 |
| 4 | Recognition ceremony | ≤2 weeks | Certificate issued | → Step 5 |
| 5 | R&R leave approval | ≤2 weeks | Leave granted | → Step 6 |
| 6 | 30/90 day follow-up | 30/90 days | Recovery confirmed | → Close |