SADC HUMANITARIAN AND EMERGENCY

OPERATIONS CENTRE (SHOC)

EMERGENCY RESPONSE TEAMS

OPERATIONAL ANNEXES

Emergency Response Operations

| SOP | Focus Area | Annexes | Status |
| --- | --- | --- | --- |
| 4.1 | Mobilisation & Demobilisation of ERTs | A–F, H–I, AI–AK (11) | Updated v5.1 |
| 4.2 | In-Country Protocol | J – P, AM (8) | Updated v5.1 |
| 4.3 | Transition, Demobilisation & Post-Mission | G, Q–V, AL (8) | Updated v5.1 |
| 4.4 | Transboundary Cooperation | W – AG (11) | Updated v5.1 |
| All | Communication Security Protocol | AH (1) | Restored v2.1 |

| Field | Value |
| --- | --- |
| Total Annexes | 39 Operational Templates (Annex A – Annex AM) |
| Classification | OFFICIAL – SENSITIVE |
| Version | 5.1 – February 2026 |
| Approved By | SHOC Director / Governing Board |
| Replaces | V4 Annexes v4.0 (Feb 2026) – 39 templates in A–AH scheme |

Aligned with: IFRC Surge Toolbox | UNDAC Handbook (2024) | OSOCC Guidelines | ISO 22301:2019 | AHA Centre ERAT

# Authority and Use of Operational Annexes

### 1. Legal Authority

Issued under the authority of the SHOC Director per the SHOC Intergovernmental Memorandum of Agreement (August 2022, Kinshasa SADC Summit) and the SHOC Hosting Agreement with the Republic of Mozambique (3 April 2023).

### 2. Status of Annexes

| Classification | Description |
| --- | --- |
| MANDATORY | All annexes are mandatory operational tools for emergency response. |
| AUTHORITATIVE | Annexes take precedence over narrative SOP text during operations. |
| SIMULATION-READY | All forms designed for SIMEX and live operations. |

ERT ACTIVATION AND MOBILISATION ANNEXES

ERT Mobilisation and Demobilisation

# ANNEX A

## ERT Mobilisation Checklist

Reference: ERT ACTIVATION AND MOBILISATION | Output: MOB-CHK-01

### 1. Purpose

Ensure all actions, personnel, equipment verified before ERT deployment across activation stages.

| Document Ref: |  | Date: |  |
| --- | --- | --- | --- |
| Prepared By: |  | Mission: |  |

### 2. Pre-Mobilisation

| Item | Description | Responsible | Status |
| --- | --- | --- | --- |
| Activation received | SHOC Situation Room activation confirmed | Head of Operations | ☐ |
| Initial assessments | Hazard verification with NDMAs, ICPs, NGOs | Early Warning Officer | ☐ |
| Team notification | Preliminary alert to ERT leadership | Programme Officer | ☐ |
| Thresholds checked | myDEWETRA/INFORM activation criteria verified | Situation Room Analyst | ☐ |

### 3. Mobilisation

| Item | Description | Responsible | Status |
| --- | --- | --- | --- |
| Personnel identified | Tier 1 team selected from ERT roster | Head of Operations | ☐ |
| Equipment check | SAR, medical, ICT verified | Supply Chain Officer | ☐ |
| Transport readiness | Vehicles, flights confirmed | Deployment Coordinator | ☐ |
| Comms systems | Radios, sat-phones tested | ICT Officer | ☐ |
| Travel clearance | Visas, entry permits, NDMA facilitation | Deployment Coordinator | ☐ |
| Pre-deployment briefing | 8-component briefing completed (Annex C) | SHOC Director | ☐ |

### 4. Full Deployment

| Item | Description | Responsible | Status |
| --- | --- | --- | --- |
| OSSHOC setup | Forward coordination hub established (Annex N) | Logistics Officer | ☐ |
| Coordination confirmed | NDMA, ICPs, NGOs, private sector | ERT Field Lead | ☐ |
| Safety briefing | UNDSS guidelines, evacuation plan | Security Focal Point | ☐ |
| 72-Hour Review cycle | First review scheduled per ERT ACTIVATION AND MOBILISATION Section 7 (Mobilisation Phases) | ERT Field Lead | ☐ |

### 5. Sustained Operations

| Item | Description | Responsible | Status |
| --- | --- | --- | --- |
| Full ERT complement | Tier 2 deployed as required | Head of Operations | ☐ |
| Info management | SitReps activated (Annex L) | IM Officer | ☐ |
| Finance admin | Per diem, procurement operational | Finance Officer | ☐ |
| Performance monitoring | Individual evaluations commenced (Annex G) | ERT Field Lead | ☐ |

| Prepared By | Approved By |
| --- | --- |
| Name: ___________________________ | Name: ___________________________ |
| Designation: ____________________ | Designation: ____________________ |
| Signature: ______________________ | Signature: ______________________ |
| Date: ___________________________ | Date: ___________________________ |

# ANNEX B

## Team Readiness Evaluation Form

Reference: ERT ACTIVATION AND MOBILISATION | Output: TRE-01

### 1. Purpose

Assess personnel and equipment readiness per IFRC/UNDAC standards before deployment.

| Document Ref: |  | Date: |  |
| --- | --- | --- | --- |
| Prepared By: |  | Mission: |  |

### 2. Personnel Readiness

| Criteria | Yes | No | N/A | Notes |
| --- | --- | --- | --- | --- |
| Medical clearance valid | ☐ | ☐ | ☐ |  |
| Vaccinations complete | ☐ | ☐ | ☐ |  |
| SHOC/UNDAC/IFRC training current | ☐ | ☐ | ☐ |  |
| PPE issued | ☐ | ☐ | ☐ |  |
| Travel documents valid | ☐ | ☐ | ☐ |  |
| Security briefing completed | ☐ | ☐ | ☐ |  |
| Insurance confirmed | ☐ | ☐ | ☐ |  |
| Pre-deployment briefing attended (Annex C) | ☐ | ☐ | ☐ |  |

### 3. Equipment Readiness

| Category | Complete | Incomplete | Notes |
| --- | --- | --- | --- |
| ICT (sat-phone, laptop, radio) | ☐ | ☐ |  |
| SAR equipment | ☐ | ☐ |  |
| Medical kit | ☐ | ☐ |  |
| OSOCC/OSSHOC equipment | ☐ | ☐ |  |
| Personal mission kit | ☐ | ☐ |  |

### 4. Overall Rating

| FULLY READY | PARTIAL – Conditions | NOT READY |
| --- | --- | --- |
| ☐ | ☐ | ☐ |

| Prepared By | Approved By |
| --- | --- |
| Name: ___________________________ | Name: ___________________________ |
| Designation: ____________________ | Designation: ____________________ |
| Signature: ______________________ | Signature: ______________________ |
| Date: ___________________________ | Date: ___________________________ |

# ANNEX C

## Pre-Deployment Briefing Record

Reference: ERT ACTIVATION AND MOBILISATION Section 8 | Output: PDB-01

### 1. Purpose

Formally record completion of the mandatory 8-component Pre-Deployment Briefing for all ERT members prior to departure. This annex documents attendance, briefing delivery, and member acknowledgement.

| Document Ref: |  | Date: |  |
| --- | --- | --- | --- |
| Prepared By: |  | Mission: |  |

### 2. Briefing Details

| Field | Details |
| --- | --- |
| Briefing Date/Time |  |
| Location/Platform | ☐ SHOC Situation Room ☐ Secure Video Conference ☐ Hybrid |
| Chaired By | ☐ SHOC Director ☐ Head of Programme |
| Mission Reference |  |
| Destination Country |  |
| Expected Duration |  |

### 3. Briefing Component Delivery

| # | Component | Delivered By | Duration | Delivered | N/A |
| --- | --- | --- | --- | --- | --- |
| 1 | Disaster Profile (hazard, scale, myDEWETRA/INFORM data) | Situation Room Analyst | 15 min | ☐ | ☐ |
| 2 | Operational Objectives (mandate, KPIs, timeline) | Head of Operations | 15 min | ☐ | ☐ |
| 3 | Command Structure (SHOC–NDMA–OSSHOC lines) | Head of Operations | 10 min | ☐ | ☐ |
| 4 | Security Briefing (UNDSS level, threats, evacuation) | Security Focal Point | 15 min | ☐ | ☐ |
| 5 | Cultural/Legal Context (protocols, language, media) | SHOC Director | 10 min | ☐ | ☐ |
| 6 | Logistics/Admin (travel, visa, accommodation, IT) | Deployment Coordinator | 15 min | ☐ | ☐ |
| 7 | Welfare/Duty of Care (stress, health, rotation, family) | HR / Welfare Officer | 10 min | ☐ | ☐ |
| 8 | Sign-Off (Q&A, confirmation, mission pack issued) | SHOC Director (Chair) | 10 min | ☐ | ☐ |

### 4. ERT Member Attendance and Acknowledgement

| # | Name | Role/Specialism | Signature | Date |
| --- | --- | --- | --- | --- |
| 1 |  |  |  |  |
| 2 |  |  |  |  |
| 3 |  |  |  |  |
| 4 |  |  |  |  |
| 5 |  |  |  |  |
| 6 |  |  |  |  |
| 7 |  |  |  |  |
| 8 |  |  |  |  |
| 9 |  |  |  |  |
| 10 |  |  |  |  |

### 5. Mission Information Pack Issued

Each ERT member received: ☐ Mission Order  ☐ Country Brief  ☐ Security Pack  ☐ Contact List  ☐ SOP Quick Reference Guide  ☐ Travel Documents

| Prepared By | Approved By |
| --- | --- |
| Name: ___________________________ | Name: ___________________________ |
| Designation: ____________________ | Designation: ____________________ |
| Signature: ______________________ | Signature: ______________________ |
| Date: ___________________________ | Date: ___________________________ |

# ANNEX D

## Travel and Entry Clearance Tracker

Reference: ERT ACTIVATION AND MOBILISATION Section 6 | Output: TEC-01

### 1. Purpose

Track visa, travel, and entry clearance status for all ERT members during mobilisation. Resolves Thabo Ndlovu Comment #28 regarding ERT travel and clearance matters.

| Document Ref: |  | Date: |  |
| --- | --- | --- | --- |
| Prepared By: |  | Mission: |  |

### 2. ERT Travel Status

| # | Name | Nationality | Passport Valid | Visa Status | Flight Booked | Insurance | Cleared |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 |  |  | ☐ Y ☐ N | ☐ Approved ☐ Pending ☐ N/A | ☐ Y ☐ N | ☐ Y | ☐ Y ☐ N |
| 2 |  |  | ☐ Y ☐ N | ☐ Approved ☐ Pending ☐ N/A | ☐ Y ☐ N | ☐ Y | ☐ Y ☐ N |
| 3 |  |  | ☐ Y ☐ N | ☐ Approved ☐ Pending ☐ N/A | ☐ Y ☐ N | ☐ Y | ☐ Y ☐ N |
| 4 |  |  | ☐ Y ☐ N | ☐ Approved ☐ Pending ☐ N/A | ☐ Y ☐ N | ☐ Y | ☐ Y ☐ N |
| 5 |  |  | ☐ Y ☐ N | ☐ Approved ☐ Pending ☐ N/A | ☐ Y ☐ N | ☐ Y | ☐ Y ☐ N |
| 6 |  |  | ☐ Y ☐ N | ☐ Approved ☐ Pending ☐ N/A | ☐ Y ☐ N | ☐ Y | ☐ Y ☐ N |
| 7 |  |  | ☐ Y ☐ N | ☐ Approved ☐ Pending ☐ N/A | ☐ Y ☐ N | ☐ Y | ☐ Y ☐ N |
| 8 |  |  | ☐ Y ☐ N | ☐ Approved ☐ Pending ☐ N/A | ☐ Y ☐ N | ☐ Y | ☐ Y ☐ N |

### 3. NDMA Facilitation

| Item | Status / Details |
| --- | --- |
| NDMA Visa Facilitation Letter Sent | ☐ Yes ☐ No Date: ________ |
| NDMA Liaison Officer Designated | Name: ______________ Phone: ______________ |
| Airport/Border Reception Confirmed | ☐ Yes ☐ No Location: ________ |
| COVID/Health Entry Requirements | ☐ N/A ☐ Met ☐ Pending |

### 4. Issues / Escalation

| # | Issue | Action Required | Responsible | Resolved |
| --- | --- | --- | --- | --- |
| 1 |  |  |  | ☐ |
| 2 |  |  |  | ☐ |
| 3 |  |  |  | ☐ |

| Prepared By | Approved By |
| --- | --- |
| Name: ___________________________ | Name: ___________________________ |
| Designation: ____________________ | Designation: ____________________ |
| Signature: ______________________ | Signature: ______________________ |
| Date: ___________________________ | Date: ___________________________ |

# ANNEX E

## Demobilisation Inventory and Handover Form

Reference: ERT ACTIVATION AND MOBILISATION & 4.3 | Output: DEM-INV-01

### 1. Purpose

Document equipment return, asset reconciliation, and formal handover during demobilisation.

| Document Ref: |  | Date: |  |
| --- | --- | --- | --- |
| Prepared By: |  | Mission: |  |

### 2. Inventory Reconciliation

| Item | Qty Deployed | Qty Returned | Condition | Notes |
| --- | --- | --- | --- | --- |
|  |  |  | ☐ Good ☐ Fair ☐ Damaged |  |
|  |  |  | ☐ Good ☐ Fair ☐ Damaged |  |
|  |  |  | ☐ Good ☐ Fair ☐ Damaged |  |
|  |  |  | ☐ Good ☐ Fair ☐ Damaged |  |
|  |  |  | ☐ Good ☐ Fair ☐ Damaged |  |

### 3. Handover to Authorities

| Item/Asset | Receiving Authority | Representative | Date | Signature |
| --- | --- | --- | --- | --- |

### 4. Team Demobilisation Status

| Member | Role | Departure Date | Status |
| --- | --- | --- | --- |
|  |  |  | ☐ Departed ☐ Pending |
|  |  |  | ☐ Departed ☐ Pending |
|  |  |  | ☐ Departed ☐ Pending |
|  |  |  | ☐ Departed ☐ Pending |

| Prepared By | Approved By |
| --- | --- |
| Name: ___________________________ | Name: ___________________________ |
| Designation: ____________________ | Designation: ____________________ |
| Signature: ______________________ | Signature: ______________________ |
| Date: ___________________________ | Date: ___________________________ |

# ANNEX F

## Close-Out Meeting Minutes Template

Reference: POST-MISSION PHASES §Close-Out Meeting | Output: COM-MIN-01

### 1. Purpose

Record the proceedings and decisions of the Close-Out Meeting (distinct from the AAR). The Close-Out Meeting is an operational handover event conducted 7 to 3 days before end of mission before ERT departure, co-chaired by ERT Field Lead and NDMA Director.

| Document Ref: |  | Date: |  |
| --- | --- | --- | --- |
| Prepared By: |  | Mission: |  |

### 2. Meeting Details

| Field | Details |
| --- | --- |
| Date/Time |  |
| Location |  |
| Chair | ERT Field Lead: _________________ |
| Co-Chair | NDMA Director: _________________ |
| Attendees |  |

### 3. 8-Point Agenda Record

| # | Agenda Item | Key Decisions/Outcomes | Action Owner | Deadline |
| --- | --- | --- | --- | --- |
| 1 | Operational Summary |  |  |  |
| 2 | Sector Handover Confirmation |  |  |  |
| 3 | Data/Information Transfer |  |  |  |
| 4 | Asset Inventory Reconciliation |  |  |  |
| 5 | Partner Continuation Plan |  |  |  |
| 6 | Outstanding Risks & Mitigation |  |  |  |
| 7 | Community Communication Plan |  |  |  |
| 8 | Formal Sign-Off & Handover |  |  |  |

### 4. Outstanding Actions

| # | Action | Responsible | Deadline | Status |
| --- | --- | --- | --- | --- |
| 1 |  |  |  | ☐ Open |
| 2 |  |  |  | ☐ Open |
| 3 |  |  |  | ☐ Open |

### 5. Formal Handover Confirmation

The ERT Field Lead and NDMA Director confirm that all operational functions have been formally handed over as documented above.

| ERT Field Lead | NDMA Director |
| --- | --- |
| Signature: ___________________ | Signature: ___________________ |
| Date: ________________________ | Date: ________________________ |

| Prepared By | Approved By |
| --- | --- |
| Name: ___________________________ | Name: ___________________________ |
| Designation: ____________________ | Designation: ____________________ |
| Signature: ______________________ | Signature: ______________________ |
| Date: ___________________________ | Date: ___________________________ |

# ANNEX G

## Individual ERT Performance Evaluation Form

Reference: POST-MISSION PHASES Phase 5 | Output: PERF-EVAL-01

### 1. Purpose

Structured assessment of individual deployed ERT member performance using the 5-domain competency framework with 360-degree feedback. Exceeds UNDAC, IFRC ERU, and AHA Centre comparator standards.

| Document Ref: |  | Date: |  |
| --- | --- | --- | --- |
| Prepared By: |  | Mission: |  |

### 2. Evaluation Details

| Field | Details |
| --- | --- |
| ERT Member Name |  |
| Role / Specialism |  |
| Mission Reference |  |
| Deployment Period |  |
| Evaluation Point | ☐ Mid-Mission (Day 10–14) ☐ End-of-Mission ☐ Post-Mission Consolidation |
| Primary Evaluator |  |

### 3. Competency Assessment (5-Point Scale: 1=Unsatisfactory, 2=Below, 3=Meets, 4=Exceeds, 5=Outstanding)

| Domain (Weight) | Criteria Summary | 1 | 2 | 3 | 4 | 5 | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1. Technical/Specialist (30%) | Expertise; quality of outputs; methodology | ☐ | ☐ | ☐ | ☐ | ☐ |  |
| 2. Coordination/Teamwork (25%) | NDMA/ICP coordination; cluster work; conflict resolution | ☐ | ☐ | ☐ | ☐ | ☐ |  |
| 3. Communication/Reporting (20%) | SitRep quality; verbal clarity; IM platform use | ☐ | ☐ | ☐ | ☐ | ☐ |  |
| 4. Professional Conduct (15%) | Code of Conduct; cultural sensitivity; initiative | ☐ | ☐ | ☐ | ☐ | ☐ |  |
| 5. Adaptability/Resilience (10%) | Performance under pressure; flexibility; self-care | ☐ | ☐ | ☐ | ☐ | ☐ |  |

### 4. 360-Degree Feedback Sources

| Source | Name | Rating (1–5) | Key Comments |
| --- | --- | --- | --- |
| ERT Field Lead (primary) |  |  |  |
| NDMA Liaison |  |  |  |
| Peer ERT Member |  |  |  |
| Head of Operations |  |  |  |

### 5. Overall Score and Roster Action

| Field | Details |
| --- | --- |
| Weighted Score | ___ / 5.0 |
| Roster Recommendation | ☐ ≥4.0 Priority deployment ☐ 3.0–3.9 Standard roster ☐ <3.0 Improvement plan ☐ <2.0 any domain: Remedial |
| Development Recommendations |  |
| ERT Member Comments |  |

Classification: OFFICIAL – SENSITIVE. Filed in SHOC ERT Database.

| Prepared By | Approved By |
| --- | --- |
| Name: ___________________________ | Name: ___________________________ |
| Designation: ____________________ | Designation: ____________________ |
| Signature: ______________________ | Signature: ______________________ |
| Date: ___________________________ | Date: ___________________________ |

# ANNEX H

## After-Action Report Template

Reference: ERT ACTIVATION AND MOBILISATION & 4.3 | Output: AAR-01

### 1. Purpose

Structured review of mission performance. The AAR is an analytical learning exercise conducted AFTER demobilisation (7 to 21 days after demobilisation), distinct from the Close-Out Meeting.

| Document Ref: |  | Date: |  |
| --- | --- | --- | --- |
| Prepared By: |  | Mission: |  |

### 2. Mission Overview

| Field | Details |
| --- | --- |
| Mission Name |  |
| Duration |  |
| Location(s) |  |
| AAR Participants |  |
| AAR Date |  |

### 3. Objectives vs Outcomes

| Objective | Achieved? | Evidence/Notes |
| --- | --- | --- |
|  | ☐ Yes ☐ Partial ☐ No |  |
|  | ☐ Yes ☐ Partial ☐ No |  |
|  | ☐ Yes ☐ Partial ☐ No |  |

### 4. What Went Well

| Area | Description | Enabling Factors |
| --- | --- | --- |

### 5. What Could Be Improved

| Area | Description | Root Cause | Recommendation |
| --- | --- | --- | --- |

### 6. Key Lessons

| # | Lesson | Action Required | Owner |
| --- | --- | --- | --- |
| 1 |  |  |  |
| 2 |  |  |  |
| 3 |  |  |  |

### 7. SOP Revision Recommendations

| # | SOP Section | Proposed Change | Priority | Owner |
| --- | --- | --- | --- | --- |
| 1 |  |  | ☐ High ☐ Med ☐ Low |  |
| 2 |  |  | ☐ High ☐ Med ☐ Low |  |

| Prepared By | Approved By |
| --- | --- |
| Name: ___________________________ | Name: ___________________________ |
| Designation: ____________________ | Designation: ____________________ |
| Signature: ______________________ | Signature: ______________________ |
| Date: ___________________________ | Date: ___________________________ |

# ANNEX I

## Lessons Learned Capture Form

Reference: ERT ACTIVATION AND MOBILISATION & 4.3 | Output: LL-01

### 1. Purpose

Capture operational lessons for SHOC knowledge management and continuous improvement.

| Document Ref: |  | Date: |  |
| --- | --- | --- | --- |
| Prepared By: |  | Mission: |  |

### 2. Mission Summary

| Field | Details |
| --- | --- |
| Deployment Type | ☐ Rapid ☐ Full ERT ☐ Support ☐ SIMEX |
| Duration |  |
| Stakeholders |  |
| Hazard |  |

### 3. What Worked Well

| Area | Description | Contributing Factors |
| --- | --- | --- |

### 4. What Did Not Work Well

| Area | Description | Root Cause |
| --- | --- | --- |

### 5. Priority Recommendations

| Priority | Recommendation | Responsible | Timeline |
| --- | --- | --- | --- |
| High |  |  |  |
| Medium |  |  |  |
| Low |  |  |  |

| Prepared By | Approved By |
| --- | --- |
| Name: ___________________________ | Name: ___________________________ |
| Designation: ____________________ | Designation: ____________________ |
| Signature: ______________________ | Signature: ______________________ |
| Date: ___________________________ | Date: ___________________________ |

IN- COUNTRY OPERATIONS PROTOCOL ANNEXES

In-Country Operations Protocol

# ANNEX J

## ERT In-Country Integration Checklist

Reference: IN- COUNTRY OPERATIONS PROTOCOL Phase 1–2 | Output: ICI-01

### 1. Purpose

Systematic integration of SHOC ERT into national coordination system upon arrival.

| Document Ref: |  | Date: |  |
| --- | --- | --- | --- |
| Prepared By: |  | Mission: |  |

### 2. Arrival Phase

| Task | Responsible | Done | Notes |
| --- | --- | --- | --- |
| Immigration/customs clearance | ERT Field Lead | ☐ |  |
| NDMA reception contact established | ERT Field Lead | ☐ |  |
| Security briefing received from NDMA | All Team | ☐ |  |
| Accommodation confirmed | Logistics Officer | ☐ |  |
| Comms systems tested in-country | ICT Officer | ☐ |  |

### 3. Integration Phase

| Task | Responsible | Done | Notes |
| --- | --- | --- | --- |
| National EOC liaison established | ERT Field Lead | ☐ |  |
| NDMA coordination meeting attended | ERT Field Lead | ☐ |  |
| ICP/NGO/Private sector coordination | ERT Field Lead | ☐ |  |
| Cluster registration completed | ERT Specialists | ☐ |  |
| OSSHOC/RDC registration (if applicable) | ERT Field Lead | ☐ |  |
| Mission objectives confirmed with NDMA | ERT Field Lead | ☐ |  |
| UNDSS security registration | All Team | ☐ |  |

| Prepared By | Approved By |
| --- | --- |
| Name: ___________________________ | Name: ___________________________ |
| Designation: ____________________ | Designation: ____________________ |
| Signature: ______________________ | Signature: ______________________ |
| Date: ___________________________ | Date: ___________________________ |

# ANNEX K

## EOC Liaison Contact List (Restricted)

Reference: IN- COUNTRY OPERATIONS PROTOCOL Phase 2 | Output: EOC-CL-01

### 1. Purpose

Restricted contacts for National EOC liaison. NOT FOR PUBLIC DISTRIBUTION.

| Document Ref: |  | Date: |  |
| --- | --- | --- | --- |
| Prepared By: |  | Mission: |  |

### 2. National EOC Contacts

| Function | Name | Phone | Email | Location |
| --- | --- | --- | --- | --- |
| EOC Director |  |  |  |  |
| Operations Chief |  |  |  |  |
| Planning Chief |  |  |  |  |
| Logistics Chief |  |  |  |  |
| Communications |  |  |  |  |

### 3. SHOC Liaison Points

| Function | Name | Phone | Email |
| --- | --- | --- | --- |
| SHOC ERT Field Lead |  |  |  |
| Operations Liaison |  |  |  |
| IM Liaison |  |  |  |
| Logistics Liaison |  |  |  |

### 4. ICP/NGO/Private Sector Contacts

| Organisation | Contact | Phone | Email |
| --- | --- | --- | --- |
| OCHA |  |  |  |
| IFRC |  |  |  |
| WFP |  |  |  |
| UNHCR |  |  |  |

| Prepared By | Approved By |
| --- | --- |
| Name: ___________________________ | Name: ___________________________ |
| Designation: ____________________ | Designation: ____________________ |
| Signature: ______________________ | Signature: ______________________ |
| Date: ___________________________ | Date: ___________________________ |

# ANNEX L

## Situation Report (SitRep) Template

Reference: ERT ACTIVATION AND MOBILISATION & 4.2 | Output: SITREP-01

### 1. Purpose

Standardised situation reporting for SHOC, NDMA, and ICP coordination. Produced every 24 hours or on request during active operations.

| Document Ref: |  | Date: |  |
| --- | --- | --- | --- |
| Prepared By: |  | Mission: |  |

### 2. Header

| SitRep # | Date/Time | Location | Prepared By |
| --- | --- | --- | --- |

### 3. Situation Overview

| Field | Details |
| --- | --- |
| Hazard Event |  |
| Location(s) |  |
| Population Affected |  |
| Current Phase | ☐ Phase 1 ☐ Phase 2 ☐ Phase 3 ☐ Phase 4 ☐ Phase 5 |

### 4. Needs Assessment

| Sector | Priority Needs | Gaps |
| --- | --- | --- |
| Shelter |  |  |
| WASH |  |  |
| Health |  |  |
| Food Security |  |  |
| Protection |  |  |

### 5. Logistics & Safety

| Field | Details |
| --- | --- |
| Assets Deployed |  |
| Transport Status |  |
| UNDSS Level | ☐ 1 ☐ 2 ☐ 3 ☐ 4 ☐ 5 |
| Security Incidents |  |
| Evacuation Status |  |

### 6. Next Steps

| Action | Responsible | Timeline | Status |
| --- | --- | --- | --- |
|  |  |  | ☐ |
|  |  |  | ☐ |
|  |  |  | ☐ |

| Prepared By | Approved By |
| --- | --- |
| Name: ___________________________ | Name: ___________________________ |
| Designation: ____________________ | Designation: ____________________ |
| Signature: ______________________ | Signature: ______________________ |
| Date: ___________________________ | Date: ___________________________ |

# ANNEX M

## Joint Assessment Template

Reference: IN- COUNTRY OPERATIONS PROTOCOL Phase 3 | Output: JA-01

### 1. Purpose

Standardised joint assessment with national authorities and ICPs following UNDAC methodology.

| Document Ref: |  | Date: |  |
| --- | --- | --- | --- |
| Prepared By: |  | Mission: |  |

### 2. Assessment Information

| Field | Details |
| --- | --- |
| Type | ☐ Rapid ☐ Detailed ☐ Sectoral ☐ Multi-Sector |
| Date(s) |  |
| Area(s) |  |
| Team |  |
| Lead Agency |  |

### 3. Sectoral Findings

| Sector | Affected Pop | Priority Needs | Gaps | Recommendations |
| --- | --- | --- | --- | --- |
| Shelter |  |  |  |  |
| WASH |  |  |  |  |
| Health |  |  |  |  |
| Food Security |  |  |  |  |
| Protection |  |  |  |  |
| Education |  |  |  |  |

### 4. Cross-Cutting Issues

| Issue | Observations | Recommendations |
| --- | --- | --- |
| Gender |  |  |
| Age (Children/Elderly) |  |  |
| Disability |  |  |
| Environment |  |  |

| Prepared By | Approved By |
| --- | --- |
| Name: ___________________________ | Name: ___________________________ |
| Designation: ____________________ | Designation: ____________________ |
| Signature: ______________________ | Signature: ______________________ |
| Date: ___________________________ | Date: ___________________________ |

# ANNEX N

## OSSHOC Establishment Checklist

Reference: IN- COUNTRY OPERATIONS PROTOCOL Phase 2 | Output: OSSHOC-01

### 1. Purpose

Checklist for establishing the On-Site SADC Humanitarian Operations Centre (OSSHOC) as the forward coordination hub at disaster site.

| Document Ref: |  | Date: |  |
| --- | --- | --- | --- |
| Prepared By: |  | Mission: |  |

### 2. Site Selection

| Criterion | Assessment |
| --- | --- |
| Proximity to NDMA EOC | ☐ Adjacent ☐ Within 30 min ☐ Other: ____ |
| Security Assessment | ☐ Secure ☐ Concerns: ____ |
| ICT Connectivity | ☐ Internet ☐ Satellite ☐ Radio ☐ None |
| Accessibility | ☐ Road ☐ Air ☐ Both |
| Space for Operations | ☐ Adequate ☐ Constrained |

### 3. Infrastructure Setup

| Item | Responsible | Status | Notes |
| --- | --- | --- | --- |
| Workspace (tents/building) | Logistics Officer | ☐ Done |  |
| Generator / Power supply | Logistics Officer | ☐ Done |  |
| ICT systems (internet, radio, sat-phone) | ICT Officer | ☐ Done |  |
| Maps / Whiteboard / Display | IM Officer | ☐ Done |  |
| Signage (SHOC / OSSHOC branding) | Logistics Officer | ☐ Done |  |
| Meeting space | Logistics Officer | ☐ Done |  |
| myDEWETRA access configured | Situation Room Analyst | ☐ Done |  |

### 4. Coordination Setup

| Task | Responsible | Done | Notes |
| --- | --- | --- | --- |
| NDMA liaison officer co-located | ERT Field Lead | ☐ |  |
| ICP/NGO coordination schedule agreed | ERT Field Lead | ☐ |  |
| Daily briefing time/location set | ERT Field Lead | ☐ |  |
| SHOC Situation Room link established | ICT Officer | ☐ |  |

| Prepared By | Approved By |
| --- | --- |
| Name: ___________________________ | Name: ___________________________ |
| Designation: ____________________ | Designation: ____________________ |
| Signature: ______________________ | Signature: ______________________ |
| Date: ___________________________ | Date: ___________________________ |

# ANNEX O

## Risk Log Template

Reference: IN- COUNTRY OPERATIONS PROTOCOL All Phases | Output: RISK-01

### 1. Purpose

Track and manage operational risks throughout mission lifecycle using the BGYOR scale.

| Document Ref: |  | Date: |  |
| --- | --- | --- | --- |
| Prepared By: |  | Mission: |  |

### 2. Risk Register

| ID | Risk Description | Category | L | I | Mitigation | Owner | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| R01 |  | ☐ Security ☐ Health ☐ Ops ☐ Logistics | ☐L ☐M ☐H | ☐L ☐M ☐H |  |  | ☐ Open ☐ Closed |
| R02 |  | ☐ Security ☐ Health ☐ Ops ☐ Logistics | ☐L ☐M ☐H | ☐L ☐M ☐H |  |  | ☐ Open ☐ Closed |
| R03 |  | ☐ Security ☐ Health ☐ Ops ☐ Logistics | ☐L ☐M ☐H | ☐L ☐M ☐H |  |  | ☐ Open ☐ Closed |
| R04 |  | ☐ Security ☐ Health ☐ Ops ☐ Logistics | ☐L ☐M ☐H | ☐L ☐M ☐H |  |  | ☐ Open ☐ Closed |
| R05 |  | ☐ Security ☐ Health ☐ Ops ☐ Logistics | ☐L ☐M ☐H | ☐L ☐M ☐H |  |  | ☐ Open ☐ Closed |

### 3. BGYOR Risk Matrix

| BLUE | GREEN | YELLOW | ORANGE | RED |
| --- | --- | --- | --- | --- |
| Minimal | Low | Moderate | High | Critical |

| Prepared By | Approved By |
| --- | --- |
| Name: ___________________________ | Name: ___________________________ |
| Designation: ____________________ | Designation: ____________________ |
| Signature: ______________________ | Signature: ______________________ |
| Date: ___________________________ | Date: ___________________________ |

# ANNEX P

## Community Engagement Plan Template

Reference: IN- COUNTRY OPERATIONS PROTOCOL Phase 5 | Output: CEP-01

### 1. Purpose

Develop joint community engagement strategy with NDMA, integrating local structures, indigenous knowledge, feedback mechanisms, and protection of vulnerable groups.

| Document Ref: |  | Date: |  |
| --- | --- | --- | --- |
| Prepared By: |  | Mission: |  |

### 2. Community Context

| Field | Details |
| --- | --- |
| Location(s) |  |
| Population |  |
| Local Languages |  |
| Key Community Structures |  |
| Cultural Protocols |  |
| Vulnerable Groups Identified |  |

### 3. Engagement Activities

| Activity | Target Group | Lead | Timing | Status |
| --- | --- | --- | --- | --- |
| Community meetings / town halls |  |  |  | ☐ |
| Risk communication (local language) |  |  |  | ☐ |
| Feedback/complaint mechanisms |  |  |  | ☐ |
| Protection assessments |  |  |  | ☐ |
| Indigenous knowledge integration |  |  |  | ☐ |

### 4. Communication Channels

| Channel | Audience | Frequency |
| --- | --- | --- |
| Community radio |  |  |
| SMS/Mobile |  |  |
| Printed materials |  |  |
| Community focal points |  |  |
| Social media (coordinated with NDMA) |  |  |

| Prepared By | Approved By |
| --- | --- |
| Name: ___________________________ | Name: ___________________________ |
| Designation: ____________________ | Designation: ____________________ |
| Signature: ______________________ | Signature: ______________________ |
| Date: ___________________________ | Date: ___________________________ |

POST-MISSION PHASES ANNEXES

Transition, Demobilisation & Post-Mission Reporting

# ANNEX Q

## Handover Report Template

Reference: POST-MISSION PHASES Phase 2 | Output: HOR-01

### 1. Purpose

Formal documentation of operational handover during transition phase.

| Document Ref: |  | Date: |  |
| --- | --- | --- | --- |
| Prepared By: |  | Mission: |  |

### 2. Handover Details

| Field | Details |
| --- | --- |
| Handover Date |  |
| Handing Over Officer |  |
| Receiving Authority/Officer |  |
| Location |  |
| Witness(es) |  |

### 3. Operational Status at Handover

| Area | Status | Outstanding Items | Notes |
| --- | --- | --- | --- |
| Response Operations | ☐ Complete ☐ Ongoing |  |  |
| Coordination | ☐ Complete ☐ Ongoing |  |  |
| Information Management | ☐ Complete ☐ Ongoing |  |  |
| Logistics | ☐ Complete ☐ Ongoing |  |  |
| Finance | ☐ Complete ☐ Ongoing |  |  |

### 4. Assets & Equipment Handed Over

| Item | Qty | Condition | Serial/ID | Received By |
| --- | --- | --- | --- | --- |
|  |  | ☐ Good ☐ Fair ☐ Poor |  |  |
|  |  | ☐ Good ☐ Fair ☐ Poor |  |  |
|  |  | ☐ Good ☐ Fair ☐ Poor |  |  |

### 5. Documentation Transferred

| Document Type | Quantity | Format | Received By |
| --- | --- | --- | --- |
| SitReps |  | ☐ Hard ☐ Digital |  |
| Assessment Reports |  | ☐ Hard ☐ Digital |  |
| Financial Records |  | ☐ Hard ☐ Digital |  |
| Coordination Logs |  | ☐ Hard ☐ Digital |  |

| Prepared By | Approved By |
| --- | --- |
| Name: ___________________________ | Name: ___________________________ |
| Designation: ____________________ | Designation: ____________________ |
| Signature: ______________________ | Signature: ______________________ |
| Date: ___________________________ | Date: ___________________________ |

# ANNEX R

## End-of-Mission Report Template

Reference: POST-MISSION PHASES Phase 5 | Output: EOM-01

### 1. Purpose

Comprehensive final report documenting entire mission lifecycle and outcomes. Submitted within 30 days of demobilisation.

| Document Ref: |  | Date: |  |
| --- | --- | --- | --- |
| Prepared By: |  | Mission: |  |

### 2. Mission Data

| Field | Details |
| --- | --- |
| Mission Name |  |
| Location(s) |  |
| Duration |  |
| Team Size |  |
| Hazard Type |  |
| Population Reached |  |

### 3. Executive Summary

(Narrative field – max 500 words)

### 4. Operational Achievements

| # | Achievement | Sector | Evidence |
| --- | --- | --- | --- |
| 1 |  |  |  |
| 2 |  |  |  |
| 3 |  |  |  |

### 5. Challenges and Lessons

| # | Challenge | Impact | Lesson/Recommendation |
| --- | --- | --- | --- |
| 1 |  |  |  |
| 2 |  |  |  |
| 3 |  |  |  |

### 6. Financial Summary

| Budget Line | Allocated | Spent | Variance |
| --- | --- | --- | --- |
| Personnel |  |  |  |
| Travel |  |  |  |
| Equipment |  |  |  |
| Operations |  |  |  |
| TOTAL |  |  |  |

| Prepared By | Approved By |
| --- | --- |
| Name: ___________________________ | Name: ___________________________ |
| Designation: ____________________ | Designation: ____________________ |
| Signature: ______________________ | Signature: ______________________ |
| Date: ___________________________ | Date: ___________________________ |

# ANNEX S

## AAR Template (Comprehensive)

Reference: POST-MISSION PHASES Phase 4 | Output: AAR-02

### 1. Purpose

Comprehensive After-Action Review template for the formal AAR conducted 7 to 21 days after demobilisation after demobilisation. Co-chaired by SHOC Director and NDMA Director. Uses the 4-component methodology.

| Document Ref: |  | Date: |  |
| --- | --- | --- | --- |
| Prepared By: |  | Mission: |  |

### 2. AAR Details

| Field | Details |
| --- | --- |
| Mission Reference |  |
| AAR Date(s) |  |
| Chair | SHOC Director: _______________ |
| Co-Chair | NDMA Director: _______________ |
| Participants |  |
| Facilitator |  |

### 3. Component 1: What Was Planned?

| Question | Response |
| --- | --- |
| Mission objectives |  |
| Plan of Action |  |
| Resources allocated |  |
| Timeline |  |

### 4. Component 2: What Actually Happened?

| Question | Response |
| --- | --- |
| Achievements vs plan |  |
| Divergence from plan |  |
| Actual timeline |  |
| Unexpected events |  |

### 5. Component 3: Why?

| Factor | Contribution to Success | Contribution to Challenge |
| --- | --- | --- |
| SOP adequacy |  |  |
| Training/preparedness |  |  |
| Coordination mechanisms |  |  |
| Resources/logistics |  |  |
| Partner coordination |  |  |
| Systemic issues |  |  |

### 6. Component 4: How to Improve?

| # | Recommendation | SOP/Process Affected | Owner | Priority | Deadline |
| --- | --- | --- | --- | --- | --- |
| 1 |  |  |  | ☐ H ☐ M ☐ L |  |
| 2 |  |  |  | ☐ H ☐ M ☐ L |  |
| 3 |  |  |  | ☐ H ☐ M ☐ L |  |
| 4 |  |  |  | ☐ H ☐ M ☐ L |  |

| Prepared By | Approved By |
| --- | --- |
| Name: ___________________________ | Name: ___________________________ |
| Designation: ____________________ | Designation: ____________________ |
| Signature: ______________________ | Signature: ______________________ |
| Date: ___________________________ | Date: ___________________________ |

# ANNEX T

## Financial Reconciliation Form

Reference: POST-MISSION PHASES Phase 3 | Output: FIN-REC-01

### 1. Purpose

Reconcile all mission expenditure including per diem, travel, equipment, and operational costs.

| Document Ref: |  | Date: |  |
| --- | --- | --- | --- |
| Prepared By: |  | Mission: |  |

### 2. Budget Summary

| Budget Line | Budgeted | Actual | Variance | Notes |
| --- | --- | --- | --- | --- |
| Personnel (per diem, allowances) |  |  |  |  |
| Travel (flights, ground transport) |  |  |  |  |
| Equipment & supplies |  |  |  |  |
| Communications |  |  |  |  |
| Accommodation |  |  |  |  |
| Insurance |  |  |  |  |
| Miscellaneous |  |  |  |  |
| TOTAL |  |  |  |  |

### 3. Outstanding Items

| # | Item | Amount | Status | Expected Resolution |
| --- | --- | --- | --- | --- |
| 1 |  |  | ☐ Pending ☐ Approved |  |
| 2 |  |  | ☐ Pending ☐ Approved |  |

| Prepared By | Approved By |
| --- | --- |
| Name: ___________________________ | Name: ___________________________ |
| Designation: ____________________ | Designation: ____________________ |
| Signature: ______________________ | Signature: ______________________ |
| Date: ___________________________ | Date: ___________________________ |

# ANNEX U

## Knowledge Repository Submission Guide

Reference: POST-MISSION PHASES Phase 5 | Output: KR-01

### 1. Purpose

Guide for submitting all mission documentation to the SHOC Knowledge Repository for long-term preservation.

| Document Ref: |  | Date: |  |
| --- | --- | --- | --- |
| Prepared By: |  | Mission: |  |

### 2. Submission Checklist

| Document | Format | Submitted | Date |
| --- | --- | --- | --- |
| Mission Order | ☐ PDF ☐ DOCX | ☐ |  |
| All SitReps | ☐ PDF ☐ DOCX | ☐ |  |
| Assessment Reports | ☐ PDF ☐ DOCX | ☐ |  |
| AAR Report (Annex S) | ☐ PDF ☐ DOCX | ☐ |  |
| Lessons Learned (Annex I) | ☐ PDF ☐ DOCX | ☐ |  |
| Financial Reconciliation (Annex T) | ☐ PDF ☐ DOCX | ☐ |  |
| Performance Evaluations (Annex G) | ☐ PDF ☐ DOCX | ☐ |  |
| Close-Out Minutes (Annex F) | ☐ PDF ☐ DOCX | ☐ |  |
| Handover Report (Annex Q) | ☐ PDF ☐ DOCX | ☐ |  |
| GIS/Map Products | ☐ GIS ☐ PDF | ☐ |  |
| Photo/Media Archive | ☐ Digital folder | ☐ |  |

### 3. Archive Verification

| Field | Details |
| --- | --- |
| Archive Reference Number |  |
| Verified By |  |
| Classification | OFFICIAL – SENSITIVE |
| Retention Period | Permanent |

| Prepared By | Approved By |
| --- | --- |
| Name: ___________________________ | Name: ___________________________ |
| Designation: ____________________ | Designation: ____________________ |
| Signature: ______________________ | Signature: ______________________ |
| Date: ___________________________ | Date: ___________________________ |

# ANNEX V

## Close-Out Meeting Agenda Template

Reference: POST-MISSION PHASES Close-Out Meeting | Output: COA-01

### 1. Purpose

Standardised agenda for the Close-Out Meeting. This meeting is an operational handover event, DISTINCT from the After-Action Review (AAR). Conducted 7 to 3 days before end of mission before ERT departure.

| Document Ref: |  | Date: |  |
| --- | --- | --- | --- |
| Prepared By: |  | Mission: |  |

### 2. Meeting Information

| Field | Details |
| --- | --- |
| Date/Time |  |
| Location |  |
| Chair: ERT Field Lead |  |
| Co-Chair: NDMA Director |  |

### 3. Agenda

| # | Item | Content | Led By | Duration |
| --- | --- | --- | --- | --- |
| 1 | Operational Summary | Mission achievements; population reached; sectors covered; milestones | ERT Field Lead | 15 min |
| 2 | Sector Handover | Status per sector; receiving entity; outstanding actions; resource transfer | Sector Specialists | 30 min |
| 3 | Data/Information Transfer | Assessment data; contacts; GIS products; SitRep archives to NDMA | IM Officer | 10 min |
| 4 | Asset Inventory | Reconciliation of all equipment; handover or return to SHOC | Logistics Officer | 15 min |
| 5 | Partner Continuation | Ongoing ICP/NGO/private sector activities; coordination handover | ICP Representatives | 15 min |
| 6 | Outstanding Risks | Remaining gaps; mitigation plans; escalation procedures | ERT Field Lead + NDMA | 15 min |
| 7 | Community Communication | Communication plan for affected communities; complaint mechanisms | NDMA Director | 10 min |
| 8 | Formal Sign-Off | Handover confirmation; signing of Handover Report; acknowledgements | ERT Field Lead + NDMA | 10 min |

Total estimated duration: 2 hours

Output documents: Signed Handover Report (Annex Q), Close-Out Minutes (Annex F), Partner Continuation Plan, Asset Transfer Register

| Prepared By | Approved By |
| --- | --- |
| Name: ___________________________ | Name: ___________________________ |
| Designation: ____________________ | Designation: ____________________ |
| Signature: ______________________ | Signature: ______________________ |
| Date: ___________________________ | Date: ___________________________ |

TRANSBOUNDARY COOPERATION ANNEXES

Transboundary Cooperation

# ANNEX W

## CBCC Terms of Reference

Reference: TRANSBOUNDARY COOPERATION Coordination | Output: CBCC-TOR-01

### 1. Purpose

Establish governance framework for the Cross-Border Coordination Cell during multi-country emergencies.

| Document Ref: |  | Date: |  |
| --- | --- | --- | --- |
| Prepared By: |  | Mission: |  |

### 2. Composition

| Role | Member State/Org | Name | Contact |
| --- | --- | --- | --- |
| CBCC Chair (SHOC) |  |  |  |
| Country A Focal Point |  |  |  |
| Country B Focal Point |  |  |  |
| Country C Focal Point |  |  |  |
| ICP Representative |  |  |  |
| SHOC IM Officer |  |  |  |

### 3. Functions

Coordinate joint assessments across borders; harmonise response activities; share situation information and early warning; facilitate cross-border movement of humanitarian personnel and goods; produce consolidated multi-country SitReps; coordinate with regional and international partners.

### 4. Operating Procedures

| Item | Specification |
| --- | --- |
| Meeting Frequency | ☐ Daily ☐ Twice Weekly ☐ Weekly |
| Meeting Platform | ☐ In-person ☐ Virtual ☐ Hybrid |
| Reporting Line | SHOC Head of Operations |
| Decision Authority | Consensus; escalation to NDMA Directors |
| Working Languages | English, French, Portuguese |

### 5. Activation and Deactivation

| Field | Details |
| --- | --- |
| Activation Trigger | Cross-border emergency declaration by 2+ Member States |
| Activation Authority | SHOC Director |
| Deactivation Criteria | Joint determination that cross-border coordination no longer required |
| Deactivation Authority | SHOC Head of Operations with NDMA concurrence |

| Prepared By | Approved By |
| --- | --- |
| Name: ___________________________ | Name: ___________________________ |
| Designation: ____________________ | Designation: ____________________ |
| Signature: ______________________ | Signature: ______________________ |
| Date: ___________________________ | Date: ___________________________ |

# ANNEX X

## Cross-Border SitRep Template

Reference: TRANSBOUNDARY COOPERATION Reporting | Output: CB-SITREP-01

### 1. Purpose

Multi-country situation report compiled by CBCC from all CB Desk inputs. Produced every 24 hours.

| Document Ref: |  | Date: |  |
| --- | --- | --- | --- |
| Prepared By: |  | Mission: |  |

### 2. Header

| CB SitRep # | Date/Time | Countries Covered | Compiled By |
| --- | --- | --- | --- |

### 3. Situation by Country

| Country | Affected Pop | Key Developments | Priority Needs | Cross-Border Issues |
| --- | --- | --- | --- | --- |

### 4. Cross-Border Coordination Status

| Item | Status |
| --- | --- |
| Humanitarian corridors |  |
| Joint assessments |  |
| Shared logistics |  |
| Population movement |  |
| Joint communication |  |

| Prepared By | Approved By |
| --- | --- |
| Name: ___________________________ | Name: ___________________________ |
| Designation: ____________________ | Designation: ____________________ |
| Signature: ______________________ | Signature: ______________________ |
| Date: ___________________________ | Date: ___________________________ |

# ANNEX Y

## Joint Operations Plan Template

Reference: TRANSBOUNDARY COOPERATION Phase 2 | Output: CB-JOP-01

### 1. Purpose

Framework for coordinated cross-border response operations. Developed within 48 hours of CBCC activation.

| Document Ref: |  | Date: |  |
| --- | --- | --- | --- |
| Prepared By: |  | Mission: |  |

### 2. JOP Overview

| Field | Details |
| --- | --- |
| JOP Reference |  |
| Emergency |  |
| Countries Covered |  |
| Period Covered |  |
| Lead Coordination | CBCC / SHOC |

### 3. Unified Objectives

| # | Objective | Lead Country/Agency | Timeline |
| --- | --- | --- | --- |
| 1 |  |  |  |
| 2 |  |  |  |
| 3 |  |  |  |

### 4. Cross-Border Logistics

| Corridor | Countries Connected | Status | Lead |
| --- | --- | --- | --- |
|  |  | ☐ Open ☐ Restricted ☐ Closed |  |
|  |  | ☐ Open ☐ Restricted ☐ Closed |  |

### 5. Resource Allocation

| Resource | Providing Country/Org | Receiving Country | Status |
| --- | --- | --- | --- |

| Prepared By | Approved By |
| --- | --- |
| Name: ___________________________ | Name: ___________________________ |
| Designation: ____________________ | Designation: ____________________ |
| Signature: ______________________ | Signature: ______________________ |
| Date: ___________________________ | Date: ___________________________ |

# ANNEX Z

## Cross-Border Data-Sharing Agreement Template

Reference: TRANSBOUNDARY COOPERATION Phase 3 | Output: CB-DSA-01

### 1. Purpose

Formal agreement for sharing disaster data between affected Member States through the CBCC, including data protection and archiving standards.

| Document Ref: |  | Date: |  |
| --- | --- | --- | --- |
| Prepared By: |  | Mission: |  |

### 2. Parties

| Party | Representative |
| --- | --- |
| Country A NDMA |  |
| Country B NDMA |  |
| SHOC / CBCC |  |

### 3. Data Types and Protocols

| Data Type | Classification | Sharing Platform | Update Frequency |
| --- | --- | --- | --- |
| Hazard monitoring | ☐ Open ☐ Restricted |  |  |
| Population displacement | ☐ Open ☐ Restricted |  |  |
| Needs assessment | ☐ Open ☐ Restricted |  |  |
| Logistics corridor | ☐ Open ☐ Restricted |  |  |

### 4. Data Protection

All personal data processed in accordance with applicable national data protection legislation and SADC data governance frameworks. Personal data anonymised before cross-border sharing. Retention period: aligned with SHOC Knowledge Repository standards.

| Prepared By | Approved By |
| --- | --- |
| Name: ___________________________ | Name: ___________________________ |
| Designation: ____________________ | Designation: ____________________ |
| Signature: ______________________ | Signature: ______________________ |
| Date: ___________________________ | Date: ___________________________ |

# ANNEX AA

## Cross-Border After-Action Review (CB-AAR) Template

Reference: TRANSBOUNDARY COOPERATION Review | Output: CB-AAR-01

### 1. Purpose

Structured review of cross-border coordination effectiveness. Conducted within 21 days of CBCC deactivation. Findings integrated into POST-MISSION PHASES mission-level AAR.

| Document Ref: |  | Date: |  |
| --- | --- | --- | --- |
| Prepared By: |  | Mission: |  |

### 2. CB-AAR Details

| Field | Details |
| --- | --- |
| Emergency Reference |  |
| Countries |  |
| CBCC Active Period |  |
| CB-AAR Date |  |
| Chair | SHOC Director |
| Participants |  |

### 3. Cross-Border Coordination Assessment

| Area | 1 | 2 | 3 | 4 | 5=Outstanding Comments |
| --- | --- | --- | --- | --- | --- |
| CBCC activation timeliness | ☐ | ☐ | ☐ | ☐ | ☐ |
| Information sharing between countries | ☐ | ☐ | ☐ | ☐ | ☐ |
| Humanitarian corridor effectiveness | ☐ | ☐ | ☐ | ☐ | ☐ |
| Joint assessment quality | ☐ | ☐ | ☐ | ☐ | ☐ |
| Resource allocation fairness | ☐ | ☐ | ☐ | ☐ | ☐ |
| Communication across borders | ☐ | ☐ | ☐ | ☐ | ☐ |

### 4. Key Lessons and Recommendations

| # | Lesson/Recommendation | Responsible | Priority | Deadline |
| --- | --- | --- | --- | --- |
| 1 |  |  | ☐ H ☐ M ☐ L |  |
| 2 |  |  | ☐ H ☐ M ☐ L |  |
| 3 |  |  | ☐ H ☐ M ☐ L |  |

| Prepared By | Approved By |
| --- | --- |
| Name: ___________________________ | Name: ___________________________ |
| Designation: ____________________ | Designation: ____________________ |
| Signature: ______________________ | Signature: ______________________ |
| Date: ___________________________ | Date: ___________________________ |

# ANNEX AB

## Humanitarian Corridor Access Request

Reference: TRANSBOUNDARY COOPERATION Logistics | Output: HC-REQ-01

### 1. Purpose

Request form for expedited clearance of humanitarian goods and personnel through designated SADC cross-border corridors.

| Document Ref: |  | Date: |  |
| --- | --- | --- | --- |
| Prepared By: |  | Mission: |  |

### 2. Request Details

| Field | Details |
| --- | --- |
| Requesting Organisation |  |
| Corridor |  |
| Border Post |  |
| Date/Time of Crossing |  |
| Purpose |  |

### 3. Goods Manifest

| Item Description | Quantity | Value (USD) | HS Code | Hazardous? |
| --- | --- | --- | --- | --- |
|  |  |  |  | ☐ Y ☐ N |
|  |  |  |  | ☐ Y ☐ N |
|  |  |  |  | ☐ Y ☐ N |
|  |  |  |  | ☐ Y ☐ N |

### 4. Personnel

| Name | Nationality | Passport # | Role |
| --- | --- | --- | --- |

| Prepared By | Approved By |
| --- | --- |
| Name: ___________________________ | Name: ___________________________ |
| Designation: ____________________ | Designation: ____________________ |
| Signature: ______________________ | Signature: ______________________ |
| Date: ___________________________ | Date: ___________________________ |

# ANNEX AC

## Cross-Border Risk Communication Template

Reference: TRANSBOUNDARY COOPERATION Communications | Output: CB-RISKCOMM-01

### 1. Purpose

Harmonised public information template for cross-border risk communication in English, French, and Portuguese.

| Document Ref: |  | Date: |  |
| --- | --- | --- | --- |
| Prepared By: |  | Mission: |  |

### 2. Message Details

| Field | Details |
| --- | --- |
| Hazard |  |
| Affected Countries |  |
| Target Audience |  |
| Languages | ☐ English ☐ French ☐ Portuguese ☐ Local: ____ |
| Dissemination Channels | ☐ Radio ☐ SMS ☐ Social Media ☐ Print ☐ Community |

### 3. Key Messages

| # | Message (English) | Message (French) | Message (Portuguese) |
| --- | --- | --- | --- |
| 1 |  |  |  |
| 2 |  |  |  |
| 3 |  |  |  |

### 4. Approval

| Country | Approved By / Date |
| --- | --- |
| Country A NDMA |  |
| Country B NDMA |  |
| SHOC |  |

| Prepared By | Approved By |
| --- | --- |
| Name: ___________________________ | Name: ___________________________ |
| Designation: ____________________ | Designation: ____________________ |
| Signature: ______________________ | Signature: ______________________ |
| Date: ___________________________ | Date: ___________________________ |

# ANNEX AD

## CBCC Deactivation Checklist

Reference: TRANSBOUNDARY COOPERATION Phase 5 | Output: CB-DEAC1hr before departure

### 1. Purpose

Checklist for orderly deactivation of the Cross-Border Coordination Cell and transition to bilateral/national mechanisms.

| Document Ref: |  | Date: |  |
| --- | --- | --- | --- |
| Prepared By: |  | Mission: |  |

### 2. Deactivation Criteria Verification

| Criterion | Met? | Evidence |
| --- | --- | --- |
| Cross-border coordination no longer required | ☐ Yes ☐ No |  |
| All affected states resumed full national management | ☐ Yes ☐ No |  |
| Bilateral agreements in place for ongoing coordination | ☐ Yes ☐ No |  |
| Outstanding cross-border issues resolved | ☐ Yes ☐ No |  |

### 3. Handover Actions

| Action | Responsible | Done | Notes |
| --- | --- | --- | --- |
| CB Desk officers notified | CBCC Chair | ☐ |  |
| Final CB SitRep issued | SHOC IM | ☐ |  |
| Data archives transferred | SHOC IM | ☐ |  |
| ICPs/partners notified | CBCC Chair | ☐ |  |
| CB-AAR scheduled (within 21 days) | SHOC Director | ☐ |  |
| Deactivation formally communicated to all NDMAs | SHOC Director | ☐ |  |

| Prepared By | Approved By |
| --- | --- |
| Name: ___________________________ | Name: ___________________________ |
| Designation: ____________________ | Designation: ____________________ |
| Signature: ______________________ | Signature: ______________________ |
| Date: ___________________________ | Date: ___________________________ |

# ANNEX AE

## Regional Lessons-Learnt Synthesis Report Template

Reference: TRANSBOUNDARY COOPERATION Learning | Output: CB-LL-01

### 1. Purpose

Template for the Regional Lessons-Learnt Synthesis Report, compiled within 45 days of CBCC deactivation and disseminated to all SADC NDMAs.

| Document Ref: |  | Date: |  |
| --- | --- | --- | --- |
| Prepared By: |  | Mission: |  |

### 2. Report Summary

| Field | Details |
| --- | --- |
| Emergency |  |
| Countries Affected |  |
| CBCC Active Period |  |
| Report Date |  |
| Compiled By |  |

### 3. Thematic Lessons

| Theme | Key Finding | Recommendation |
| --- | --- | --- |
| Activation & setup |  |  |
| Information sharing |  |  |
| Logistics corridors |  |  |
| Partner coordination |  |  |
| Community engagement |  |  |
| Immigration/customs |  |  |

### 4. Dissemination Record

| Recipient | Date Sent | Acknowledgement |
| --- | --- | --- |
| All 16 SADC NDMAs |  |  |
| SADC Secretariat |  |  |
| ICPs/UN agencies |  |  |
| SHOC Knowledge Repository |  |  |

| Prepared By | Approved By |
| --- | --- |
| Name: ___________________________ | Name: ___________________________ |
| Designation: ____________________ | Designation: ____________________ |
| Signature: ______________________ | Signature: ______________________ |
| Date: ___________________________ | Date: ___________________________ |

# ANNEX AF

## CBCC Organogram

Reference: TRANSBOUNDARY COOPERATION Coordination | Output: CBCC-ORG-01

### 1. Purpose

Organisational structure of the Cross-Border Coordination Cell showing reporting lines between SHOC, CBCC, CB Desks, and partner organisations.

| Document Ref: |  | Date: |  |
| --- | --- | --- | --- |
| Prepared By: |  | Mission: |  |

### 2. CBCC Structure

[Placeholder for CBCC Organisational Chart – to be rendered from PlantUML source in Repair Guide]

Structure: SHOC Director → Head of Operations → CBCC Chair → CB Desk Coordinators (per affected state) + ICP Liaison + IM Officer. Each CB Desk comprises: Coordinator, Operations Focal Point, IM Officer, Logistics Focal Point, Border Agency Liaison.

### 3. CBCC Staffing

| Position | Name | Country/Org | Contact |
| --- | --- | --- | --- |
| CBCC Chair |  | SHOC |  |
| CBCC Deputy |  |  |  |
| CB Desk Coord – Country A |  |  |  |
| CB Desk Coord – Country B |  |  |  |
| IM Officer |  | SHOC |  |
| Logistics Coordinator |  |  |  |
| ICP Liaison |  |  |  |

| Prepared By | Approved By |
| --- | --- |
| Name: ___________________________ | Name: ___________________________ |
| Designation: ____________________ | Designation: ____________________ |
| Signature: ______________________ | Signature: ______________________ |
| Date: ___________________________ | Date: ___________________________ |

# ANNEX AG

## SADC Priority Cross-Border Humanitarian Corridors Map

Reference: TRANSBOUNDARY COOPERATION Reference | Output: CB-CORR-01

### 1. Purpose

Reference map and directory of priority cross-border humanitarian corridors within the SADC region for use during transboundary operations.

| Document Ref: |  | Date: |  |
| --- | --- | --- | --- |
| Prepared By: |  | Mission: |  |

### 2. Priority Corridors

[Placeholder for SADC Priority Corridors Map – to be rendered as GIS product]

### 3. Corridor Directory

| # | Corridor Name | Countries Connected | Border Post(s) | Key Logistics Notes |
| --- | --- | --- | --- | --- |
| 1 | Beira Corridor | Mozambique – Zimbabwe – Zambia | Machipanda / Forbes | Rail + road; WFP warehouse Beira |
| 2 | Nacala Corridor | Mozambique – Malawi – Zambia | Nayuchi / Entre Lagos | Deep-water port; rail link |
| 3 | North-South Corridor | South Africa – Zimbabwe – Zambia – DRC | Beitbridge / Chirundu / Kasumbalesa | Major trade route; high volume |
| 4 | Maputo Corridor | Mozambique – South Africa – Eswatini | Ressano Garcia / Lebombo | Port access; toll road |
| 5 | Trans-Caprivi | Namibia – Zambia – Botswana | Katima Mulilo / Kazungula | Kazungula bridge (2021) |
| 6 | Dar Corridor | Tanzania – DRC – Zambia – Burundi | Tunduma / Nakonde | Alternative Indian Ocean access |

| Prepared By | Approved By |
| --- | --- |
| Name: ___________________________ | Name: ___________________________ |
| Designation: ____________________ | Designation: ____________________ |
| Signature: ______________________ | Signature: ______________________ |
| Date: ___________________________ | Date: ___________________________ |

CROSS-CUTTING ANNEX

Applicable to All SOPs

# ANNEX AH

## Communication Security Protocol

Reference: All SOPs | Output: COMMSEC-01

### 1. Purpose

Restored from ERT ACTIVATION AND MOBILISATION v1.0 per Repair Guide Recommendation D.12. Consolidates communication security provisions applicable to all four SOPs.

| Document Ref: |  | Date: |  |
| --- | --- | --- | --- |
| Prepared By: |  | Mission: |  |

### 2. Communication Channels

| Priority | Channel | Usage |
| --- | --- | --- |
| Priority 1 (Critical) | Radio, satellite phones, secure encrypted systems | Mission-critical and sensitive communications; command decisions; emergency coordination |
| Priority 2 (Routine) | Email, video conferencing, WhatsApp, Slack | Coordination meetings; SitRep dissemination; partner updates; routine planning |
| Priority 3 (General) | Telephone calls, SMS | Non-urgent updates; administrative matters; general information sharing |

### 3. Data Encryption and Access Control

| Requirement | Specification |
| --- | --- |
| Encryption | All sensitive communications encrypted (emails, video conferencing, radio transmissions containing mission-critical or personal data) |
| Access Control | Access limited to authorised personnel; levels granted according to role and function |
| Monitoring | Real-time monitoring to ensure adherence to security protocols and prevent breaches |
| Audit Trail | All communications logged with timestamp, sender, recipient, and classification level |

### 4. Communication by Activation Stage

| Stage | Primary Channel | Tools | Frequency | Key Action |
| --- | --- | --- | --- | --- |
| Monitoring | Situation Room | Sat-phone, radio, SMS, email | 1–2 hourly | Alert reaches NDMAs, ICPs, responders |
| Activation | Operations team | Radio, sat-phone, video conf, email | Ongoing | Rapid deployment coordination |
| Mobilisation | OSSHOC hub | Radio, sat-comm, Situation Room platforms | Real-time | ICP logistics and resource coordination |
| In Operation | Full network | Radio, sat-comm, Situation Room, video, email | Ongoing | Full operational coordination |

### 5. Language Protocol

Communication conducted in English, French, or Portuguese depending on regional requirements and partners. Translators available for all high-level coordination meetings and formal documentation.

### 6. Documentation Requirements

All communications during mobilisation and demobilisation documented and logged: situation reports, coordination logs, decision records, and updates on resource movements. Communication management platforms (Situation Room Platforms) used to manage and store all communication records.

| Prepared By | Approved By |
| --- | --- |
| Name: ___________________________ | Name: ___________________________ |
| Designation: ____________________ | Designation: ____________________ |
| Signature: ______________________ | Signature: ______________________ |
| Date: ___________________________ | Date: ___________________________ |

# ANNEX AI

## Mission Information Pack Template

NEW IN v3.0 — Aligned to SOP v5.1

Reference: ERT ACTIVATION AND MOBILISATION §8 | Output: MIP-01

### 1. Purpose

Standardised information pack issued to each ERT member at the conclusion of the Pre-Deployment Briefing (Annex C). The Mission Information Pack consolidates all essential mission documents, contact details, and guidance into a single, portable reference that must be carried by every ERT member throughout the deployment.

| Document Ref: |  | Date: |  |
| --- | --- | --- | --- |
| Prepared By: |  | Mission: |  |

### 2. Pack Contents Checklist

| Item | Description | Included | N/A |
| --- | --- | --- | --- |
| Mission Order Summary | One-page extract of SHOC Director mission order including: mission name, activation date, affected state, hazard type, ERT composition, expected duration | ☐ | ☐ |
| Country Hazard Profile | Current hazard briefing sheet from Situation Room: active hazards, affected areas, population at risk, access constraints, weather outlook | ☐ | ☐ |
| Contact and Escalation Matrix Card | Laminated pocket card (Annex AJ) with all key contacts and escalation pathways | ☐ | ☐ |
| NDMA DRR Focal Point Details | Name, mobile, email, WhatsApp of designated NDMA DRR Focal Point; airport reception details; arrival protocol | ☐ | ☐ |
| Travel Itinerary | Flight details, ground transport arrangements, accommodation address and contact | ☐ | ☐ |
| Visa / Entry Clearance Confirmation | Copy of visa approval or NDMA entry facilitation letter (from Annex D) | ☐ | ☐ |
| Security Briefing Summary | UNDSS threat level, movement restrictions, evacuation assembly points, emergency numbers, medevac protocol | ☐ | ☐ |
| Code of Conduct / PSEA Acknowledgement | Signed copy of Code of Conduct acknowledgement and PSEA declaration | ☐ | ☐ |
| Communication Security Protocol | Extract of Annex AH relevant to mission: channel priorities, | ☐ | ☐ |
| FAQ and Troubleshooting Guide | Common questions: flight cancellation, lost passport, illness in transit, arrival procedures, accommodation queries, security reporting | ☐ | ☐ |
| Map Pack | Operational area map, affected area map, OSSHOC/EOC location, key facilities, evacuation routes | ☐ | ☐ |
| Personal Asset Register | List of SADC assets issued to the individual member (IT equipment, comms devices, PPE, specialist tools) with serial numbers | ☐ | ☐ |

### 3. Pack Issue Record

| Field | Details |
| --- | --- |
| ERT Member Name |  |
| ERT Role / Designation |  |
| Pack Serial Number | MIP-______-______ |
| Issued By |  |
| Issue Date and Time |  |
| Member Signature (Acknowledgement of Receipt) |  |

### 4. Notes

(a) The Mission Information Pack must be carried at all times during transit and deployment. (b) Lost or damaged packs must be reported immediately to the ERT Field Lead. (c) Pack contents are classified OFFICIAL – SENSITIVE and must not be shared with unauthorised persons. (d) Digital copies are available on the SHOC ERT Portal under the mission record.

| Prepared By | Approved By |
| --- | --- |
| Name: ___________________________ Designation: ____________________ Signature: ______________________ Date: ___________________________ | Name: ___________________________ Designation: ____________________ Signature: ______________________ Date: ___________________________ |

# ANNEX AJ

## Contact and Escalation Matrix Card

NEW IN v3.0 — Aligned to SOP v5.1

Reference: ERT ACTIVATION AND MOBILISATION §10 | Output: CEM-01

### 1. Purpose

Pocket-size reference card issued to every ERT member as part of the Mission Information Pack (Annex AI). Answers the core question: “Who do I speak to or contact for what problem?” This card must be carried at all times during deployment.

| Document Ref: |  | Date: |  |
| --- | --- | --- | --- |
| Prepared By: |  | Mission: |  |

### 2. Mission Contact Directory

| Role | Name | Mobile / Sat-Phone | Email |
| --- | --- | --- | --- |
| SHOC Director |  |  |  |
| ERT Coordinator (Head of Ops) |  |  |  |
| NDMA DRR Focal Point |  |  |  |
| ERT Field Lead |  |  |  |
| Logistics Officer |  |  |  |
| Security Focal Point |  |  |  |
| IM Officer |  |  |  |
| HR / Welfare Officer |  |  |  |
| SHOC Situation Room (24/7) |  |  |  |
| UNDSS Country Office |  |  |  |
| Medical Emergency |  |  |  |

### 3. Escalation Matrix

| Problem / Situation | First Contact | Escalation | Portal Action |
| --- | --- | --- | --- |
| Mission order query | ERT Coordinator | SHOC Director | View mission order on Portal |
| Availability or deployment restriction | ERT Coordinator | SHOC Director | Update availability on Portal |
| Travel disruption (flight cancelled, delay) | SHOC HR / Deployment Coordinator | ERT Coordinator | HR logs rebooking on Portal |
| Lost passport or travel document | SHOC HR / Deployment Coordinator | NDMA DRR Focal Point (for entry) | Emergency ID via Portal |
| Visa or entry clearance issue | NDMA DRR Focal Point | ERT Coordinator → SHOC Director | Clearance tracker on Portal |
| Security concern or threat | ERT Field Lead | Security Focal Point → SHOC Director | Security incident report |
| Medical emergency (personal) | ERT Field Lead | HR/Welfare Officer → SHOC Director | Medical evacuation protocol |
| PSEA complaint | ERT Field Lead | NDMA Director or SHOC Director | Confidential reporting channel |
| Operational disagreement with NDMA | ERT Field Lead | ERT Coordinator → SHOC Director | Log in 72-Hour Review |
| Equipment failure or shortage | Logistics Officer | ERT Coordinator | Logistics request on Portal |
| Personal welfare concern | HR / Welfare Officer | SHOC Director | Welfare log (confidential) |
| Anything else / unknown | ERT Coordinator (SHOC hours) or ERT Field Lead (in-country) | SHOC Director | General enquiry on Portal |

### 4. Emergency Numbers

| Service | Number | Notes |
| --- | --- | --- |
| Local Emergency Services |  |  |
| Nearest Hospital / Clinic |  |  |
| UNDSS Warden |  |  |
| Embassy / High Commission |  |  |
| SHOC Situation Room (24/7) |  |  |

Card Serial: CEM-______-______ | Issued: ____________ | Member Signature: ____________

| Prepared By | Approved By |
| --- | --- |
| Name: ___________________________ Designation: ____________________ Signature: ______________________ Date: ___________________________ | Name: ___________________________ Designation: ____________________ Signature: ______________________ Date: ___________________________ |

# ANNEX AK

## ERT Field Lead Pre-Deployment Checklist

NEW IN v3.0 — Aligned to SOP v5.1

Reference: ERT ACTIVATION AND MOBILISATION §11 | Output: FLPD-01

### 1. Purpose

Specific checklist for the ERT Field Lead covering responsibilities that must be completed before departure. Supplements the general ERT Mobilisation Checklist (Annex A) with Field Lead-specific obligations.

| Document Ref: |  | Date: |  |
| --- | --- | --- | --- |
| Prepared By: |  | Mission: |  |

### 2. Pre-Departure Actions (72 hours to departure)

| # | Action | Deadline | Status | Notes |
| --- | --- | --- | --- | --- |
| 1 | Confirm personal availability to ERT Coordinator within 24 hours of notification | 72hr before departure | ☐ |  |
| 2 | Sign attestation: Code of Conduct, medical fitness, conflict-of-interest declaration, PSEA acknowledgement | 72hr before departure | ☐ |  |
| 3 | Attend full Pre-Deployment Briefing (all 9 components per ERT ACTIVATION AND MOBILISATION §8) | 48hr before departure | ☐ |  |
| 4 | Review and sign Pre-Deployment Briefing Record (Annex C) | 48hr before departure | ☐ |  |
| 5 | Convene ERT team set-up meeting: confirm roles, communication protocols, reporting lines | 36hr before departure | ☐ |  |
| 6 | Verify team composition against mission order; confirm all members have valid travel documents and visas (cross-check Annex D) | 36hr before departure | ☐ |  |
| 7 | Verify personal mission kit completeness: ICT equipment, sat-phone, PPE, personal medical kit | 24hr before departure | ☐ |  |
| 8 | Confirm receipt of Mission Information Pack (Annex AI) for self and all team members | 24hr before departure | ☐ |  |
| 9 | (Annex AJ) issued to all team members | 24hr before departure | ☐ |  |
| 10 | Confirm travel logistics: flights, ground transport, accommodation details with SHOC HR / Deployment Coordinator | 24hr before departure | ☐ |  |
| 11 | Confirm communication with NDMA DRR Focal Point: arrival time, reception point, arrival protocol, initial briefing schedule | 12hr before departure | ☐ |  |
| 12 | Confirm security briefing acknowledged and evacuation plan understood by all team members | 12hr before departure | ☐ |  |
| 13 | Declare any spouse/partner on same deployment to ERT Coordinator | 12hr before departure | ☐ |  |
| 14 | Final check: SHOC ERT Portal status updated to MOBILISED; all personal documents verified | departure day | ☐ |  |
| 15 | Assume transit command; ensure all team members accounted for at departure point | departure day | ☐ |  |

### 3. In-Transit Responsibilities

| # | Action | Status | Notes |
| --- | --- | --- | --- |
| 1 | Maintain headcount of all ERT members during transit | ☐ |  |
| 2 | Ensure team has emergency contact numbers accessible during transit | ☐ |  |
| 3 | Contact NDMA DRR Focal Point with updated ETA upon boarding and upon landing | ☐ |  |
| 4 | Report any transit disruptions immediately to ERT Coordinator | ☐ |  |
| 5 | Confirm team arrival to SHOC Situation Room upon reaching destination | ☐ |  |

### 4. Field Lead Declaration

I confirm that all pre-deployment actions listed above have been completed and that the ERT is ready for deployment.

| Prepared By | Approved By |
| --- | --- |
| Name: ___________________________ Designation: ____________________ Signature: ______________________ Date: ___________________________ | Name: ___________________________ Designation: ____________________ Signature: ______________________ Date: ___________________________ |

# ANNEX AL

## Asset Management and Reconciliation Checklist

NEW IN v5.1 — Added in v5.1

Reference: POST-MISSION PHASES Phase 3A | Output: AMRC-01

### 1. Purpose

Systematic accounting, condition assessment, and disposition of all SADC-provided, loaned, and consumable assets deployed during an ERT mission. This checklist must be completed before any ERT member departs the mission area. The ERT Logistics Officer is responsible for completion under ERT Field Lead supervision.

| Document Ref: |  | Date: |  |
| --- | --- | --- | --- |
| Prepared By: |  | Mission: |  |

### 2. Mission Asset Summary

| Field | Details |
| --- | --- |
| Mission Name / Code |  |
| Deployment Start Date |  |
| Demobilisation Date |  |
| ERT Logistics Officer |  |
| ERT Field Lead |  |
| Total Assets Deployed (from dispatch manifest) |  |

### 3. Asset Register — Physical Inventory (3 to 2 days before departure)

Cross-reference each item against the SHOC ERT Portal asset module / dispatch manifest (ERT ACTIVATION AND MOBILISATION Step 8).

| # | Asset Tag / Serial | Description | Classification | Qty Deployed | Qty Present | Condition | Assigned To |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 |  |  | ☐ Capital ☐ Consumable ☐ Loaned ☐ Donated |  |  | ☐ S ☐ R ☐ U ☐ C |  |
| 2 |  |  | ☐ Capital ☐ Consumable ☐ Loaned ☐ Donated |  |  | ☐ S ☐ R ☐ U ☐ C |  |
| 3 |  |  | ☐ Capital ☐ Consumable ☐ Loaned ☐ Donated |  |  | ☐ S ☐ R ☐ U ☐ C |  |
| 4 |  |  | ☐ Capital ☐ Consumable ☐ Loaned ☐ Donated |  |  | ☐ S ☐ R ☐ U ☐ C |  |
| 5 |  |  | ☐ Capital ☐ Consumable ☐ Loaned ☐ Donated |  |  | ☐ S ☐ R ☐ U ☐ C |  |
| ... |  |  |  |  |  |  |  |

Condition Key: S = Serviceable (fully functional) | R = Repairable (functional with minor defects) | U = Unserviceable (non-functional) | C = Consumed (fully used, no physical item remaining)

Classification Key: Capital = Durable equipment >USD 500 or >1 year useful life | Consumable = Fully consumed during mission | Loaned = Equipment from NDMAs/ICPs/UN/private sector requiring return | Donated = Formally transferred to host NDMA

### 4. Asset Disposition Summary (2 to 1 day before departure)

| Disposition | Qty | Est. Value (USD) | Authorising Document | Notes |
| --- | --- | --- | --- | --- |
| (a) Return to SHOC (Nacala warehouse) |  |  | This checklist |  |
| (b) Transfer to Host NDMA |  |  | Transfer of Custody Certificate + Annex E |  |
| (c) Transfer to ICP |  |  | Transfer of Custody Certificate |  |
| (d) Write-Off (lost / destroyed / beyond repair) |  |  | Loss/Damage Report (Section 5) |  |
| (e) Consumable Depletion |  |  | This checklist |  |
| TOTAL ACCOUNTED FOR |  |  |  |  |

### 5. Loss and Damage Report

Complete one row per lost, stolen, or damaged-beyond-repair asset. Attach photographic evidence and incident reports.

| Asset Tag / Serial | Description | Circumstances (date, location, personnel) | Cause | Est. Replacement Value (USD) | Evidence Attached |
| --- | --- | --- | --- | --- | --- |
|  |  |  | ☐ Operational hazard ☐ Negligence ☐ Force majeure ☐ Theft |  | ☐ Photos ☐ Incident report ☐ Witness statement |
|  |  |  | ☐ Operational hazard ☐ Negligence ☐ Force majeure ☐ Theft |  | ☐ Photos ☐ Incident report ☐ Witness statement |
|  |  |  | ☐ Operational hazard ☐ Negligence ☐ Force majeure ☐ Theft |  | ☐ Photos ☐ Incident report ☐ Witness statement |

Write-off approval: ERT Coordinator (all items) / SHOC Director (items >USD 1,000)

### 6. Reconciliation Summary

| Category | Count | Value (USD) |
| --- | --- | --- |
| Total Assets Deployed (dispatch manifest) |  |  |
| Total Assets Accounted For (sum of dispositions) |  |  |
| Discrepancy (if any) |  |  |
| Discrepancy Explanation |  |  |

### 7. Individual Asset Sign-Off

Each ERT member confirms return of all personally assigned assets. Portal status will not be updated to DEMOBILISED until this section is complete.

| ERT Member Name | Assets Assigned | Assets Returned | Discrepancy | Member Signature | Logistics Officer Signature |
| --- | --- | --- | --- | --- | --- |

### 8. Final Sign-Off

This Asset Management and Reconciliation Checklist has been completed. All assets have been accounted for through disposition categories listed in Section 4. Any discrepancies have been documented and explained.

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| ERT Logistics Officer (Completed By) |  |  |  |
| ERT Field Lead (Verified By) |  |  |  |
| ERT Coordinator (Approved By) |  |  |  |
| NDMA Director / NDMA DRR Focal Point (Countersigned) |  |  |  |

Uploaded to SHOC ERT Portal: ☐ Yes ☐ No | Date: ______________ | Uploaded By: ______________

Forms part of: Financial Reconciliation Form (Annex T) package. Retained for minimum 5 years per SADC Secretariat records management policy.

# ANNEX AM

## Operational Briefing Roster Template

NEW IN v5.1 — Added in v5.1

Reference: IN- COUNTRY OPERATIONS PROTOCOL §7A | Output: DBR-01

### 1. Purpose

Record of the mandatory daily coordination briefing between the NDMA Emergency Operations Centre and the deployed ERT. This template captures attendance, agenda items, decisions, and action items for each operational briefing session. The completed roster is uploaded to the SHOC ERT Portal within 2 hours of briefing conclusion and forms part of the permanent mission record.

| Document Ref: |  | Date: |  |
| --- | --- | --- | --- |
| Prepared By: |  | Mission: |  |

### 2. Briefing Details

| Field | Details |
| --- | --- |
| Briefing Date |  |
| Briefing Time (local) |  |
| Location (EOC / OSSHOC / Remote) |  |
| Chaired By |  |
| Briefing Number (sequential) |  |
| Briefing Format | ☐ Standard (30–45 min) ☐ Shortened (15 min) ☐ Extraordinary |

### 3. Attendance Roster

| # | Name | Organisation / Role | Mandatory / Invited | Present | Remote |
| --- | --- | --- | --- | --- | --- |
| 1 |  | NDMA Director / NDMA DRR Focal Point (Chair) | Mandatory | ☐ | ☐ |
| 2 |  | ERT Field Lead | Mandatory | ☐ | ☐ |
| 3 |  | ERT Specialist: ____________ | Mandatory | ☐ | ☐ |
| 4 |  | ERT Specialist: ____________ | Mandatory | ☐ | ☐ |
| 5 |  | ERT Specialist: ____________ | Mandatory | ☐ | ☐ |
| 6 |  | Logistics Officer | Mandatory | ☐ | ☐ |
| 7 |  | IM Officer | Mandatory | ☐ | ☐ |
| 8 |  | Security Focal Point | Mandatory (if activated) | ☐ | ☐ |
| 9 |  | ICP Representative: ____________ | Invited | ☐ | ☐ |
| 10 |  | UN Agency Liaison: ____________ | Invited | ☐ | ☐ |
| 11 |  |  | Invited | ☐ | ☐ |
| 12 |  |  | Invited | ☐ | ☐ |

Total Mandatory Attendees: _____ of _____ present | Total Invited Attendees: _____ present

### 4. Standard Agenda Record

| # | Agenda Item | Presenter | Duration | Key Points / Summary |
| --- | --- | --- | --- | --- |
| 1 | Overnight Situation Update (hazard status, population, access, security) | NDMA Situation Room / ERT IM Officer | 5–10 min |  |
| 2 | Sector / Cluster Status Reports (progress, obstacles, resource needs) | ERT Specialists (2–3 min each) | 10–15 min |  |
| 3 | Logistics and Supply Chain (incoming supplies, distribution, transport, pipeline) | Logistics Officer | 5 min |  |
| 4 | Security Update (threat level, movement restrictions, incidents) | Security Focal Point / ERT Field Lead | 5 min |  |
| 5 | Coordination Issues (inter-agency, NDMA directives, ICP engagement) | Chair / ERT Field Lead | 5–10 min |  |
| 6 | Priority Actions for Next 24 Hours (task assignments, deadlines) | NDMA Director + ERT Field Lead (joint) | 5–10 min |  |
| 7 | Welfare Check (team health, rotation scheduling) | ERT Field Lead | 2–3 min |  |

### 5. Key Decisions Taken

| # | Decision | Decided By | Effective From |
| --- | --- | --- | --- |
| 1 |  |  |  |
| 2 |  |  |  |
| 3 |  |  |  |
| 4 |  |  |  |

### 6. Action Items

| # | Action Required | Responsible Person | Deadline | Status |
| --- | --- | --- | --- | --- |
| 1 |  |  |  | ☐ Open ☐ In Progress ☐ Complete |
| 2 |  |  |  | ☐ Open ☐ In Progress ☐ Complete |
| 3 |  |  |  | ☐ Open ☐ In Progress ☐ Complete |
| 4 |  |  |  | ☐ Open ☐ In Progress ☐ Complete |
| 5 |  |  |  | ☐ Open ☐ In Progress ☐ Complete |
| 6 |  |  |  | ☐ Open ☐ In Progress ☐ Complete |

### 7. Escalation Triggers Identified

Tick any triggers requiring immediate escalation to SHOC Director / ERT Coordinator (per IN- COUNTRY OPERATIONS PROTOCOL §7A):

| Trigger | Identified? | Details / Action Taken |
| --- | --- | --- |
| (a) Critical change in hazard status / secondary hazard | ☐ |  |
| (b) Security incident affecting ERT / operational area | ☐ |  |
| (c) Significant resource / logistics shortfall (not locally resolvable) | ☐ |  |
| (d) Operational disagreement between ERT and NDMA (unresolved) | ☐ |  |
| (e) PSEA incident or serious conduct breach | ☐ |  |
| (f) Medical emergency requiring evacuation | ☐ |  |

Escalation communicated to SHOC Situation Room: ☐ Yes ☐ No ☐ N/A | Time: ____________

### 8. Next Briefing

| Field | Details |
| --- | --- |
| Next Briefing Date |  |
| Next Briefing Time |  |
| Location |  |
| Any special agenda items for next briefing |  |

### 9. Sign-Off

| Role | Name | Signature | Date / Time |
| --- | --- | --- | --- |
| Chair (NDMA Director / NDMA DRR Focal Point) |  |  |  |
| ERT Field Lead |  |  |  |
| Recorded By (ERT IM Officer) |  |  |  |

Uploaded to SHOC ERT Portal: ☐ Yes ☐ No | Upload Time: ____________ (must be within 2 hours of briefing conclusion)

This record feeds: Daily SitRep (Annex L) | 72-Hour In-Progress Review (IN- COUNTRY OPERATIONS PROTOCOL §8) | After-Action Review (POST-MISSION PHASES Phase 4)

# References

African Union Commission. (2016). Africa humanitarian policy framework. Addis Ababa, Ethiopia: African Union.

African Union Commission. (2018). Africa multi-hazard early warning and early action strategy (AMEWEAS). Addis Ababa, Ethiopia: African Union.

ASEAN Coordinating Centre for Humanitarian Assistance on Disaster Management. (2021). ASEAN emergency response and assessment team (ERAT) handbook. Jakarta, Indonesia: AHA Centre.

British Standards Institution. (2018). BS 65000: Organizational resilience. London, UK: BSI.

Caribbean Disaster Emergency Management Agency. (2014). Regional response mechanism: Standard operating procedures. Bridgetown, Barbados: CDEMA.

COMESA Secretariat. (2020). COMESA regional disaster risk management strategy. Lusaka, Zambia: COMESA.

Economic Community of West African States. (2017). ECOWAS regional disaster risk reduction strategy. Abuja, Nigeria: ECOWAS Commission.

European Commission, Directorate-General for European Civil Protection and Humanitarian Aid Operations (DG ECHO). (2020). European emergency response coordination centre (ERCC) operations manual. Brussels, Belgium: European Commission.

Ferguson, C. (2026). Grouped SOP Volume 1: Finance and accounting (working draft). Southern African Development Community Secretariat.

Ferguson, C. (2026). SOP_ERT_4_v5_1 including annexes. Southern African Development Community Secretariat.

GSMA. (2022). Mobile for humanitarian innovation: Connectivity in crises report. London, UK: GSMA.

Institute of Internal Auditors. (2017). International professional practices framework (IPPF). Altamonte Springs, FL: IIA.

Instituto Nacional de Gestão e Redução do Risco de Desastres. (2014). Lei 15/2014: Disaster management law. Maputo, Mozambique: Government of Mozambique.

Instituto Nacional de Gestão e Redução do Risco de Desastres. (2020). Emergency response operational guidelines. Maputo, Mozambique: INGD.

Instituto Nacional de Gestão e Redução do Risco de Desastres. (2021). National contingency plan of Mozambique. Maputo, Mozambique: INGD.

International Federation of Accountants. (2019). Handbook of international public sector accounting pronouncements (IPSAS). New York, NY: IFAC.

International Federation of Red Cross and Red Crescent Societies. (2018). Emergency response framework (ERF). Geneva, Switzerland: IFRC.

International Federation of Red Cross and Red Crescent Societies. (2019). Logistics standards and procedures manual. Geneva, Switzerland: IFRC.

International Federation of Red Cross and Red Crescent Societies. (2021). Surge operational toolbox. Geneva, Switzerland: IFRC.

International Monetary Fund. (2019). Fiscal transparency code. Washington, DC: IMF.

International Telecommunication Union. (2021). Emergency telecommunications handbook. Geneva, Switzerland: ITU.

International Organization for Standardization. (2018). ISO 27001: Information security management systems — Requirements. Geneva, Switzerland: ISO.

International Organization for Standardization. (2019). ISO 22301: Security and resilience — Business continuity management systems — Requirements. Geneva, Switzerland: ISO.

International Organization for Standardization. (2020). ISO 22320: Security and resilience — Emergency management — Requirements for incident response. Geneva, Switzerland: ISO.

International Organization for Standardization. (2021). ISO 31000: Risk management — Guidelines. Geneva, Switzerland: ISO.

Japan International Cooperation Agency. (2019). Nacala corridor logistics development study. Tokyo, Japan: JICA.

Nathan Associates. (2018). Transport corridors for trade and development: The Nacala case. Washington, DC: USAID.

Portos e Caminhos de Ferro de Moçambique. (2020). Nacala logistics corridor operations report. Maputo, Mozambique: CFM.

SADC Secretariat. (2016). SADC disaster risk reduction strategy and plan of action 2016–2030. Gaborone, Botswana: Southern African Development Community.

SADC Secretariat. (2019). SADC humanitarian and emergency operations centre (SHOC) establishment framework. Gaborone, Botswana: Southern African Development Community.

SADC Secretariat. (2020). SADC logistics management guidelines for humanitarian operations. Gaborone, Botswana: Southern African Development Community.

SADC Secretariat. (2021). SADC standard operating procedures for regional disaster preparedness and response. Gaborone, Botswana: Southern African Development Community.

SADC Secretariat. (2023). SADC regional risk assessment report. Gaborone, Botswana: Southern African Development Community Disaster Risk Management Unit.

SADC Secretariat. (2024). SADC financial regulations. Gaborone, Botswana: Southern African Development Community.

Sphere Association. (2018). The Sphere handbook: Humanitarian charter and minimum standards in humanitarian response. Geneva, Switzerland: Sphere Association.

United Nations Department of Safety and Security. (2019). United Nations security management system framework. New York, NY: United Nations.

United Nations Global Pulse. (2020). Data responsibility guidelines for humanitarian action. New York, NY: United Nations.

United Nations High Commissioner for Refugees. (2019). UNHCR supply chain manual. Geneva, Switzerland: UNHCR.

United Nations Office for the Coordination of Humanitarian Affairs. (2018). UNDAC field handbook (8th ed.). Geneva, Switzerland: United Nations.

United Nations Office for the Coordination of Humanitarian Affairs. (2020). Humanitarian programme cycle reference module. New York, NY: United Nations.

United States Agency for International Development. (2021). Supply chain systems strengthening for emergencies. Washington, DC: USAID.

World Bank. (2020). Southern Africa trade and transport facilitation study. Washington, DC: World Bank.

World Food Programme. (2022). Emergency logistics manual. Rome, Italy: World Food Programme.

World Health Organization. (2020). Emergency logistics and procurement guidelines. Geneva, Switzerland: World Health Organization.